## QBR Agenda
AGENDA
UNITED STATES | CANADA
Health of the Business | Health of the Business
Sales | Sales
Trends/Insights | Trends/Insights
Fraud | Operations - Program Overview
Review of activities since Dec 2025 | Transition
Current state/issues | Web/Portals
Resolutions/Recommendation | Fulfillment
Operations - Program Overview | Customer Service
Web/Portals | Card Production
Fulfillment | Reporting
Customer Service | Processor Items (placeholder)
Card Production | RAIL
Reporting
Processor Items (placeholder)
RAIL

## QBR Prep Portal
|  | PROGRAM OVERVIEW |  |  | FRAUD |  | SALES |  | MARKETING |  |  | DISTRIBUTION |  | DIGITAL |  |  | CHANNELS
|  | U.S. HEALTH OF BUSINESS |  |  | FRAUD OVERVIEW |  | U.S. - SALES |  | MARKETING ACTIVITIES |  |  | U.S. - DEALER DISTRIBUTION |  | eGIFT CARD SALES YTD |  |  | B2B - DIRECT
| FALSE | Summary |  | FALSE | Summary | FALSE | Market Update | TRUE | Websites |  | FALSE | Location Engagement | TRUE | YTD | Neil to review | TRUE | Designs
[6 empty] | FALSE | Digital Shift | TRUE | Marketing Campaigns |  | FALSE | Activations |  |  |  | TRUE | Web
JOANNA |  | U.S. - PROGRAM OVERVIEW |  |  | CURRENT STATE | FALSE | Strategic Initiatives | TRUE | Specialty Campaigns |  |  |  |  | CONSUMER PURCHASING |  | TRUE | Marketing
JULIE | TRUE | Web |  | FALSE |  | FALSE | Sales | TRUE | Promotional Campaigns |  |  | CANADA - DEALER DISTRIBUTION | TRUE | Sales Dollars |  | TRUE | US Specialty
JACKIE | FALSE | Fulfillment | [8 empty] | FALSE | Location Engagement | TRUE | Count |  | TRUE | Canada Specialty
NEIL | FALSE | Customer Service |  |  | RESOLUTIONS/RECOMMEDATIONS |  | CANADA - SALES |  | CREATIVE SAMPLING |  | FALSE | Activations | TRUE | Avg. Denominations |  | FALSE | Sales Programs
JUSTIN | FALSE | Card Production |  | FALSE |  | FALSE | Strategic Initiatives | TRUE | Physical Card Emails |  |  |  | TRUE | Avg. Order
| FALSE | Reporting |  |  |  | FALSE | Sales | TRUE | Digital Card Emails |  |  |  | TRUE | Geographical |  |  | B2B - Alliance Partners
[5 empty] | REPORTING | FALSE | Forecast | TRUE | Social Posts |  |  |  | TRUE | Designs |  | TRUE | US Designs
|  | CANADA HEALTH OF BUSINESS |  | FALSE |  |  |  | TRUE | Advertisements |  |  |  | TRUE | Card Value
| FALSE | Summary |  |  |  |  | TRENDS ¦ MARKET RESEARCH | TRUE | Collateral |  |  |  | TRUE | Transactions |  |  | B2B - Scrip
[6 empty] | FALSE | US Regulatory Changes | TRUE | Shell |  |  |  | TRUE | Dealer Locations |  | TRUE | Designs | batch activation confirmation
|  | CANADA - PROGRAM OVERVIEW |  |  |  | FALSE | Incentive Market News | [8 empty] | TRUE | US Special Offers | Confirm RaiseRight $$
| TRUE | Transition | confirm RPG CVD |  |  | FALSE | Competitors |  | CARD CREATIVE & CONCEPTS |  |  |  |  | B2B Purchasing |  | TRUE | Canada Special Offers | Still Old Design?
| TRUE | Web | [5 empty] | TRUE | Card Designs | Add new CA Design |  |  | TRUE | Sales Dollars
| FALSE | Fulfillment | [5 empty] | TRUE | New Card Ideas | Need new cards |  |  | TRUE | Count |  |  | Consumer
| FALSE | Customer Service | [5 empty] | TRUE | New Carriers | [6 empty] | TRUE | New Designs
| FALSE | Card Production | [5 empty] | TRUE | Series Ideas | [6 empty] | TRUE | Logano
| FALSE | Reporting | [13 empty] | TRUE | Road Trip
[9 empty] | REPORTING | [6 empty] | TRUE | SeGC Marketing
[8 empty] | TRUE | Paid Advertisements | Review summary
[8 empty] | TRUE | Google Analytics | Review summary | [6 empty] | Dealer/Wholesalers
[16 empty] | TRUE | Designs | Confirm CVD in Retail Market now
[16 empty] | TRUE | Displays
[16 empty] | TRUE | Card Security | Update to show new backers
[16 empty] | TRUE | Dealer Resources
[16 empty] | TRUE | Legal Compliance | Update with latest CC Information

## QBR RAIL
| QBR PREP |  |  | Updated: 080326
| Item | Issue / Action | Priority | Status | Open Date | Expected Due Date | Completion Date | LEAD at Shell | LEAD at RPG | LEAD at Shift4 | Additional Notes
UNITED STATES
CARD
| Card Packaging Options - Retail | 050626 RPG to revisit and share with Shell packaging options for retail locations, including costs. To be included in 2027 budget. 051826 Neil is gathering costs associated with more secure options. | High | In Process | 2026-05-06 | 2026-07-31 |  | Lauren | Neil | -
| New Card Designs | 010226 RPG Marketing to create new designs for Consumers - both physical and digital with physcial having priority. 060126 Final review of physical designs underway. | Low | In Process | 2026-01-02 | 2026-09-01 |  | Lauren | Julie | -
FRAUD/SECURITY
| Accertify Project @ POS |  | High | In Process | 1961-05-25 | 2026-09-01 |  | Lauren | Jackie | Elana
REGULATORY
| In-store Fraud Decals | 100325 Maryland and New Jersey have new requirements to post information on Fraud laws. Work with Card Compliant to finalize. 061226 received general signage that should be created and sent to Dealers - primarily in 5 states requiring (Delaware, New Jersey, New York, Maryland, Rhode Island. 071026 Confirming with CC that RPG can move forward with uploading document and create decal for 5 states. 072426 Awaiting final QR code from CC to utilized in decal. | Medium | In Process | 2025-10-03 | 2026-09-01 |  | Lauren | Julie | -
| Fraud Notification to Dealers | 111225 Card Compliant provided Shell with an 11 page Fraud notification. Lauren requesting the development of a condense verison that can be shared with Dealers. RPG has required CC create a 2 pager version afterwhich RPG will distribute through Dealer shipments. Insert will include a QR code that will link to the full 11 page document hosted on RPG's website. 051326 Received 2 pager from Card Compliant. Some outstanding questions remain for CC before RPG can produce and add to Dealer Shipments. Awaiting their feedback. 072426 Awaiting final QR code from CC to utilized in decal. | Medium | In Process | 2025-11-25 | 2026-09-01 |  | Lauren | Julie | -
| Fraud Awareness Checkbox on Website | 100325 CC has asked RPG to add Consumer Fraud notices in the check out process (similar to Decal that will be displayed at locations). RPG to add 2nd Checkbox for consumers on Fraud notification when purchasing on website. 051326 When CC provide final feedback on Dealer decal, RPG will add to consumer purchasing process. 080326 Kevin is working to get 11 pages on website so we can link to. | Medium | In Process | 2025-10-03 | 2026-09-01 |  | Lauren | Julie | -
WEBSITES
| SeGC Moved to RPG | 050426 Develop purchasing platform for digital on RPG website. This will support challenges faces with customer support and visbility into fraud/customer Based on progress Canada launch may be excuted first. 071526 With the Canada Digital launching moving October, RPG will move forward with US digital transition to RPG website. | Medium | In Process | 2026-05-04 | 2026-09-01 |  | Lauren | Tom? | Elana
Other
| 2027 Shell Wholesaler Conference | 050826 RPG to be Gold Sponsor at Shell's 2027 Wholesaler Conference. More information from Shell will come when next steps are required. | Low | In Process | 2026-05-08 |  |  | Lauren | Julie | -
| Prezzi - Terms | 040626 Once vetted, RPG to review with Lauren. 061726 Working with Lauren to confirm move forward. 072926 Shell approved moving forward with Prezee with terms. Pending agreements | Medium | In Process | 2026-04-06 | Fall 2026 |  | Lauren | Joanna | -
PROCESSOR
| Shift4 Internal Portal | RPG continues to need additional support from Shift4 from their portal. 040626 3 main items Customer Service, SFTP testing for Script activations, and reports that need fraud information. 051126 Awaiting for Shift4 to provide next steps/details. JACKIE "room for improvement but managing customer service challenges. Activation process IS NEEDED" NEIL "outstanding open reports need to be fixed (better reporting - inconsistencies/breaks, etc) |  | In Process |  |  |  | Lauren | Jackie / Neil | Elana | Outline any items we need to establish on RAIL for Shift4
CANADA
CARD
| New Card Designs | 060126 RPG creating new designs for Canada Digital. 080306 Final designs to be circulated for approvals. | Low | In Process | 2026-01-02 | 2026-09-01 |  | Lauren | Julie | -
WEBSITE
| B2B Portal | 022026 RPG creating a B2B portal for Canada. Shift4 $11k. September 1 launch that includes digital. 080326 Development testing underway. | Medium | In Process | 2026-02-20 | 2026-09-01 |  |  | Joanna |  | Provide update on Establishment of B2B Portal
| SeGC Product | 032026 Develop digital program for Canada. Targeting July 2026. RPG needs to be complete development, followed by testing in the coming months. 042726 Still scheduled to launch digital in July, need to ensure our website is ready ASAP for testing. 051126 RPG working with Shift4 on APIs. As well as Accertify piece. SOW coming from Shift4 on multiple issuance (bulk). 051826 Awaiting Accertify confirmation of column creation. Also still waiting for SOW from Shift4. 071526 Canada Digital launch moved October. Continue finalizing APIs with Shift4, including testing to ensure prepared for October launch. | High | In Process | 2026-03-20 | 2026-10-01 |  | Paul | Julie |  | Provide update on digital on RPG Shell CA Website
CUSTOMER SERVICE
| French Support | 050126 RPG determining proper paths to update/establish to ensure French customers are being equally supported. 062226 IVR outline confirmed, Xact to do recording. 071526 RPG onboarding new employee from Quebec to support French customers - consumer and b2b. IVR being updated accordingly. | HIGH | In Process |  |  |  |  | Jackie/Joanna |  | Provide update on customer service including IVR & French services
PROCESSOR
| EML Engagement | Determine additional product needed from EML until Shift4 is complete. Outline with EML requirements (BHN cards) 040626 Confirm when next run for BHN/EML cards. 042626 Waiting to receive new inventory requirements from BHN so rerun of EML cards can be produced. Neil/Jackie to review internal requirements to produce EML B2B/Consumer and Dealer EML/Shift4. Still waiting for successful testing of CVD on Shift4 dealer. Can Shell accept both CVD and non-CVD. 062226 All channels to Shift4 except BHN - asap. All non-CVD. EML Contract ends in April. |  | In Process |  | Spring 2027? |  | Paul | Joanna | - | Provide any updates on EML relationship and plans
| Shift4 Internal Portal | Set up digital within portal (exists). Need to do testing to ensure all is available and properly working. Roundtable with Shift4 needed. WAITING FOR PAUL to schedule meeting to determine what reporting is required. |  | Not Started |  |  |  |  | Neil |  | Outline any items we need to establish on RAIL for Shift4
OTHER
| Auto Replenishment Process Review | Determine if any changes are needed to improve Auto Replenishment process including potential audits to ensure all is working properly 051126 RPG working on establishing audit to ensure functioning properly. Asking Shift4 for Onboarding process on New Stations. Kevin checking with John on EML new station data we receive. |  | In Process |  |  |  |  | Jackie |  | Provide update on Auto Replenishment processes
COMPLETED

## RPG
|  | R A I L Rolling Action Item List |  |  |  | Updated: 060826
No. | Area | Item | Issue / Action | Priority | Brand | Status | Open Date | Expected Due Date | Revised Due Date | Completion Date | LEAD at RPG | Additional Notes
| Website | RPG Website | Support IT in finalizing and launching the new RPG Website. Connect with Kevin to understand status and requirements for completion. 040626 Project has been pushed back as other projects have taken priority. Will resume when IT resources become available. | Medium | RPG | [5 empty] | Julie / Kevin
| Systems | ERP - US | 040626 Working on getting licenses finalized for update. Followed by finalizing production testing. | Medium | RPG |  |  | 2026-06-01 |  |  | Neil / Jackie | Rob to do addition testing of process flow.
| Systems | ERP - Canada | 040626 Developers are testing, followed by RPG testing. | Medium | RPG |  |  | 2026-10-01 |  |  | Neil / Jackie
| Brands | Canada Brands | Working to build out Canada brands for sales/marketing. More to come 040626 TDC has provided API credentials. Jackie confirming if portal access is required. | Low | RPG | [5 empty] | Dan / Joanna | Ivanhoe, Sobey's, TDC/Zuluna, Subway, BuyaTab/SVS
| Systems | BHN (US) | Activate via APIs with BHN (US) for inactive product + new/more products. 040626 Kevin confirming credentials for Kroger so we can test. Followed by other brands. | Low | RPG | [5 empty] | Jackie / Kevin
| Website | AMEX Website | Fraud updates to AMEX websites | Low | RPG | [5 empty] | Jackie / Kevin
COMPLETED
| Product | Nvidia Fulfillment Program | Nvidia Gift Card Fulfillment Program. 040626 confirming quantities, Nvidia wants to know if card number is on the cards. Likely to send product to their distribution center. 051126 All inventory sent to them. | Low | Nvidia | Closed |  |  |  |  | Joanna / Jackie
| Website | AMEX Website | Update websites - update disclaimers and pricing outline for Wynn, Irvine, and Epic |  | RPG | Complete

## US
|  | R A I L Rolling Action Item List |  |  |  | Updated: 071126 |  |  |  |  | INTERNAL
No. | Area | Item | Issue / Action | Include in External RAIL? | Priority | Status | Open Date | Expected Due Date | Revised Due Date | Completion Date | LEAD at Shell | LEAD at RPG | LEAD at Shift4 | Additional Notes
| Contract | Shell US #2 Amendment | Establish savings model for Strategic Partnership/Shell Entities when Erin reengages. Likely to follow after Canada is finalized. | N |  | Not Started | 2025-12-15 | 2026-06-30 |  |  | Lauren/ Erin | Julie/ Joanna | - | In additional, new amendment should have changes based on Processor items (Neil to review)
| Card Security | Card Packaging Options - Retail | RPG to revisit and share with Shell packaging options for retail locations, including costs. Lauren would like to evaluate and include in the 2027 budget. See previous submission during QBRs. 051826 Julie provided sample options, Neil to get costs from printer(s). 070626 Neil reviewing and determining inventory and costs per Lauren's request. | Y | High | In Process | 2026-05-06 | 2026-06-30 |  |  | Lauren | Neil
| Fraud | Accertify Management | RPG to support management of the Shell's Accertify relationship. 032326 Would like to connect with Lauren to see where she's at (in her head). 042726 Meetings with week with Shell (Erin/Lauren) for Lauren to chat through her intentions with Accerify team. Followed by meeting with Accerify. Afterwhich, RPG should be in a better position to determine SOW/Contract Amendment with Accertify & Shell. 050426 Waiting for pricing from Accertify and Shift4 is working on SOW. 051126 Jackie received failed transaction files and she will be sharing Accertify. RPG to be established as a Reseller - pending feedback from Shell. 062226 Accertify provided pricing to Shell - Lauren/Erin reviewing, plan to request reduction in costs - more to come 062926 Jackie meeting with Zach to review Terry thoughts on Reseller agreement. | N |  | In Process |  |  |  |  | Lauren | Jackie | -
| Regulatory | State Fraud Decals | Maryland and New Jersey have new requirements to post information on Fraud laws. Work with Card Compliant to finalize. 050426 sent Card Compliant email request final details on required signage. 061226 received general signage that should be created and sent to Dealers - primarily in 5 states requiring (Delaware, New Jersey, New York, Maryland, Rhode Island. 071026 Confirming with CC that RPG can move forward with uploading document and create decal for 5 states. | Y |  | In Process | 2025-10-03 |  |  |  |  | Julie | -
| Regulatory | Fraud Regulation Notification to Dealers | Card Compliant to provide a 1-2 page version for RPG to included in Dealer shipments (would include link to full 11 pager). 031126 RPG requested update from CC. 051326 CC provided, Julie to work on piece to send to Dealers. 062226 Need to create link on SGC website to download 11 page doc. that is only available via QR code provided to Dealers in 2 page insert. Inserts will be sent to Dealers within their shipments. 071026 Provided Kevin with .pdf to add to Shell US website. Once uploaded add QR code to 2 pager and begin to distribute in Dealer shipments. | Y |  | In Process | 2025-11-12 | 2026-06-01 |  |  |  | Julie | -
| Card | Card Designs | Marketing to create new designs for Consumers. | N |  | In Process | 2026-01-02 | 2026-06-30 |  |  |  | Julie | -
| Card | eCard Designs | Marketing to create seasonal designs for Consumers. | N |  | In Process | 2026-01-02 | 2026-06-30 |  |  |  | Julie | Simone
| Website | SeGC Moved to RPG | Building SeGC purchasing on RPG's Shell website. 050426 Will wait to launch SeGC in the US until after Canada digital is launched. | N |  | Not Started | [5 empty] | Tom?
| QBR | Summer QBR (Chicago) | Begin preparation for QBR. Shift4 to be included. Possibility August (Sox/Mets game/August). Locking into week of August 24 - waiting for Tom to confirm date of game. 062226 QBR officially on August 26th (Wednesday). More to come. | Y |  | In Process | [5 empty] | Julie
| Website | Fraud Terms Checkbox on Website | Card Compliant requesting purchasing customers acknowledge fraud information has been provided to them. Pending finalized version from CC. | Y |  | In Process | [5 empty] | Julie | -
| Customer | Prezzi - Terms | Once vetted, RPG needs to get Lauren to agree to view Prezzi like AAP and allow for terms. More information should be coming from Tom. 051426 Working with Tom to confirm request to Shell. 062926 Discussion with Shell has happen, pending Lauren's feedback. To view Prezzi as 3rd Party, also keep rev share. 070626 Joanna to reconnect with Lauren for follow up | N |  | Awaiting | 2026-04-06 |  |  |  |  | Tom / Joanna
| Processor | Shift4 Internal Portal | RPG continues to need additional support from Shift4 from their portal. 040626 3 main items Customer Service, SFTP testing for Script activations, and reports that need fraud information. 051126 Awaiting for Shift4 to provide next steps/details. | N |  | In Process | [5 empty] | Jackie / Neil
| Conference | Shell Wholesaler Conference 2027 | Marketing to prepare for Sponsorship, details to come shortly. Pending information from Lauren. Tom approved Gold Sponsorship - moving forward with Lauren. | Y |  | In Process | [5 empty] | Julie | -
| Website | ADA Compliance | Bring Shell sites up to date with ADA compliance. Received request from Corporate customer to ensure our site meets compliance. IT working on. 050426 website is 85% compliant, finalizing + to include B2B portal. 051126 Kevin to review B2B timeline. | N | High | In Process | 2026-04-20 | 2026-04-24 |  |  | - | Kevin | -
QUESTIONS
For | Item | Question | [5 empty] | Notes
COMPLETED
| Card | InComm Card Testing | Finalize testing of InComm cards. 032326 RPG testing is complete. Missing Best Buy in this run. Westrock should be producing shortly. Westrock is in process of shipping out. | Internal ONLY |  | Complete | [5 empty] | Jackie
| Card | BHN Card Testing | Finalize testing of BHN cards. 032326 RPG testing is complete. Westrock should be producing shortly. Westrock is in process of shipping out. | Internal ONLY |  | Complete | [5 empty] | Jackie
| Reporting | Fraud numbers to Card Compliant | Neil to immedately provide Card Compliant Fraud numbers to Card Compliant. Based on card replacements by month. Additionally work to provide CC quantity of card replacements. 051226 Neil has supplied CC with Fraud numbers by month for 2025. Additionally, he will be sending CC monthly sales numbers. Same report he sends to Shell. | Y | High | Complete | 2026-04-30 | 2026-05-08 |  | 2026-05-12 |  | Neil

## Canada
|  | R A I L Rolling Action Item List |  |  |  | Updated: 071026 |  |  |  |  | INTERNAL
No. | Area | Item | Issue / Action | Include in External RAIL? | Priority | Status | Open Date | Expected Due Date | Revised Due Date | Completion Date | LEAD at Shell | LEAD at RPG | LEAD at Shift4 | Additional Notes
| Contract | Shell Canada Amendment | Working with Paul/Erin on amendment. Submitted updated pricing that includes savings for Strategic Partners, etc. 021926 submitted pricing sheet and details to Paul/Erin. 032326 Erin responded she and Paul are working on some feedback internally and they will set up a time to discuss in the next couple of weeks. 042926 Checked in with Erin, she will be circling back with Paul to review. 062226 Confirming with Erin, contract terms understanding of end date. | N | High | Awaiting Shell | 2026-02-17 | 04/0/26 |  |  | Paul/ Erin | Julie/ Joanna | -
| Processor | EML Engagement | Determine additional product needed from EML until Shift4 is complete. Outline with EML requirements (BHN cards) 040626 Confirm when next run for BHN/EML cards. 042626 Waiting to receive new inventory requirements from BHN so rerun of EML cards can be produced. Neil/Jackie to review internal requirements to produce EML B2B/Consumer and Dealer EML/Shift4. Still waiting for successful testing of CVD on Shift4 dealer. Can Shell accept both CVD and non-CVD. 062226 All channels to Shift4 except BHN - asap. All non-CVD. | N |  | In Process | [5 empty] | Joanna // Jackie | -
| Card / Website | SeGC Product | Shell looking to launch digital in Canada. Targeting July 2026. RPG needs to be complete development, followed by testing in the coming months. 042726 Still scheduled to launch digital in July, need to ensure our website is ready ASAP for testing. 051126 Kevin working with Shift4 on APIs. As well as Accertify piece. SOW coming from Shift4 on multiple issuance (bulk). Justin K reviewing. 051826 Awaiting Accertify confirmation of column creation. Also still waiting for SOW from Shift4. 062926 Digital launch moved to October. | N | High | In Process | 2026-03-20 | 2026-10-01 |  |  | Paul | Julie / Kevin
| Website | Digital eGift Card Receipient Email | 062226 RPG received links for CA App emails - need to incorporate into recipient 062926 send email template to Paul for review 071026 resent email template to Paul for review |  |  | In Process | 2026-06-22
| Website | B2B Portal | Need to launch B2B portal for Canada. Shift4 $11k. September 1 launch that includes digital. 062926 launching end of August physical, digital to come after launch in October. Need to sort out shipping connectivity. | N |  | In Process | 2026-02-20 | 2026-09-01 |  |  |  | Julie / Kevin
| Processor | Shift 4 Security and Card configuration | Support Shell Canada in determining gift card security features (CVD) and POS requirements to accommodate EML cards, existing dealer cards (no cvd) and augmented cards to be printed. | Y | High | In Process |  |  |  |  | Paul | Julie/ Joanna | Elana
| AAP | InComm 3rd Party Cards | Grocery channel, successful testing to be completed by June 5, 2026. Cards need to be in warehouse by August 21st for September in-stores. 031126 RPG finalizing artwork (Snapcard) before sending to Shell & InComm for approvals. 042726 Paul has indicated a project reset is to take place, we believe this primarily is a result of InComm costs - more to come. 050226 Artwork approved and ready for AllCard. Order data. 051126 Allcard has received artwork. Data order for test cards with CVD ordered, Incomm needs to send data to AllCard as well to marry. Test cards will go InComm. 062226 Pending Incomm activation feedback. 062926 Shell hasn't have a successful test yet. Shift4 said not activate yet, WHY? Joann needs to activate first. 070926 Shell has succesffuly tested and has provided approval for RPG to move forward with production. | Y |  | In Process |  |  |  |  | Paul | Julie
| Customer Service | French Support | Finalizing call center workflow, etc. 040626 CRM being built out now, plus email and toggliing for English/French. Continued work on Xact Level I in development. 050126 Determine proper paths to update/establish to ensure French customer are being equally supported 051126 Jackie leaving as is for now with Live agent answering call - no IVR at this time. Dealers inbox cleared out and Shell should see a reduced volume of conerns coming in. 051826 Jackie working through Xact information to improve their process, including IVR options. 062226 IVR outline confirmed, Xact to do recording. 062926 Finalizing new hire find for French CS (consumer, b2b, and retail). Joanna and Jackie to meet with her.) French IVR recording. 070626 Possible new hire for French - working with Donna | N | HIGH | In Process | [5 empty] | Jackie/ Joanna
| Auto Replenishment | Auto Replenishment Process Review | Determine if any changes are needed to improve Auto Replenishment process including potential audits to ensure all is working properly 051126 IT working on establishing audit to ensure functioning properly. Asking Shift4 for Onboarding process on New Stations. Kevin checking with John on EML new station data we receive. | N |  | In Process
| Processor | Shift4 Internal Portal | Set up digital within portal (exists). Need to do testing to ensure all is available and properly working. | N |  | Not Started | [5 empty] | Neil
| Processes | SOP | Joanna and team working on SOP documentation. 040626 draft by end of this week. | N |  | In Process |  | 2026-04-11 |  |  |  | Joanna
| Design | Retail CVD card carrier Design | Create visual (slight difference) from non CVD and CVD
| Dealers | InComm 1st Party Cards | Shell Dealers to display SGCs in InComm's mall. This is on hold. Internal politics, IT, and accounting resources needed from Shell before this can get moving again. | N |  | Hold |  |  |  |  | Paul
| Accounting | Shell Reporting Requirements | RPG ready to support Shell on additional once Shell identifies. 032326 Paul indicated he will reach out when ready. | Y |  | Hold | [5 empty] | Neil
COMPLETED
| Accounting | Customer Appeasement Account | RPG to create a goodwill account to support replacements cards. 031126 Neil is good to invoice Shell as needed. | Internal ONLY |  | Complete |  |  |  |  | - | Neil | -
| Contract | EML Extension for 1 year | Extend Agreement with EML for 1 year to allow for continued activation on EML product to accomodate IT/POS issues with activation of Shift 4 product. 032326 working on amendment with CA legal. 040626 received EML approved ready to sign shortly. | Y | High | In Process | 2026-03-11 | 2026-04-01 |  |  | Paul/ Erin | Joanna |  | Definitely Blackhawk, could use for RPG B2B and Consumer
| Card Production | Dealer | Running low on Dealer cards and will need to produce both EML and Shift4. Let's ensure we get written approval from Paul to produce more Shift4 with no CVD. 051126 confirm with Shell on CVD testing today to see if successful. RPG to determine dropdead deadline for ordering more cards. 051826 Kevin double checking no errors on auto. Neil to review inventory and trends. | Y |  | Completed | [5 empty] | Neil / Jackie
| Reporting | Sales Reporting | Can Neil provide consolidated sales reporting for 2025. To be added to waterfall. 050426 Neil to provide updates to numbers to waterfall. 051126 Neil to provide updates to numbers on waterfall. 051826 Completed - Joanna to confirm | N |  | Completed | [5 empty] | Neil / Joanna

## Shell CA Website
| R A I L Rolling Action Item List |  |  | Updated: 042026
Product | Item | Issue / Action | Priority | Status | Open Date | Expected Due Date | Revised Due Date | Completion Date | Admin. Lead | IT Lead | Additional Notes
SeGC | UI Purchasing Pages | Develop purchasing pages for website for B2C | 1st | In Process | 2026-02-17 | 04/0/26 |  |  | Julie | Kevin
SeGC | Website UX Updates | Update website content to incoporate new product (copy, images, FAQs, etc). To mirror U.S. B2C | 1st | In Process |  |  |  |  | Julie
SeGC | Accertify | Establish integration with Accertify to ensure necessary security in place for purchasing B2C. 040626 IT has begin the process to set up. Connecting with Shift4. 042726 Need Accertify applied to both Digital and Physical on the website. | 1st | In Process |  |  |  |  | Neil / Jackie
SeGC | Translations | Secure translations for all new pages in French Canadian B2C | 1st | Not Started |  |  |  |  | Julie
SeGC | Back End Processor Integration | Integration with Shift4 APIs for distribution of egift cards when purchase is complete B2C | 1st | In Process |  |  |  |  | Jackie | Kevin
SeGC | Code Delivery via Email | Establish standard email for code delivery, including both languages B2C | 1st | Not Started |  |  |  |  | Jackie / Julie
SeGC | New Product Reporting | Establish reporting items within Shift4 portal B2C | 1st | Not Started |  |  |  |  | Neil
SeGC | Testing | Execute all necessary testing including, internal and App B2C | 1st | Not Started |  |  |  |  | Jackie | Kevin
B2B Portal | Timeline | Confirm timeline for RPG Internal to develop B2B portal | 2nd | In Process |  |  |  |  | Joanna | Kevin
B2B Portal | UI Purchasing Pages | Develop B2B pages for purchase both physical and digital cards B2B portal | 2nd | In Process |  |  |  |  | Julie | Kevin
B2B Portal | Website UX Updates | Update B2B website content to improve B2B engagement B2B portal | 2nd | Not Started |  |  |  |  | Julie
B2B Portal | Back End System Integration | Integrate B2B purchasing portal with RPG CRM/Database systemB2B portal | 2nd | Not Started |  |  |  |  | Jackie | Kevin
B2B Portal | Security | Establish integration with Accertify to ensure necessary security in place for purchasing B2B portal | 2nd | Not Started
B2B Portal | Testing | Execute all necessary testing B2B portal | 2nd | Not Started
Digital purchasing features
Scheduled delivery
Multiple certificates in a single purchase
Multiple recipients within a single purchase
Dollar thresholds
Digital and reload fulfillment
Instant issuance vs. manual approval
QuickBooks sales order generation (manual vs API)
Funds capture and settlement
Consumer physcial card considerations
Purchase thresholds
Billing/shipping match requirements
Fulfillment
QUESTIONS
For | Item | Question | [5 empty] | Notes
Paul | Purchasing Min/Max | What card minimum/maximum does Shell want for consumer digital purchase. Include ask for total purchase qty/value.
Elana |  | Digital email and integration within Shift4 portal
COMPLETED

## CARD PRODUCTION
CARD PRODUCTION - US |  |  |  |  | C = COMPLETE ¦ A = APPROVED |  |  |  | Updated: 041526
No. | Channel | Processor/Type | Status | Details | Overall QTY | Dates/Timing |  | Production Process - Artwork |  |  |  | Production Process - Data |  |  |  | Production Process - Packaging/Labeling |  |  | Additional Notes
[6 empty] | Ordered | Delivery | Card Artwork | Carrier Artwork | Card Proofs | Carrier Proofs | Order Data | Data Set Up Reviewed | Processor Sends Data To Printer | Data Proof Testing | Packaging/ Labeling Set Up | Review Label Proofs | Production Label Proofs Approved
| BHN | Shift4 w/ CVD | In Production / Shipping in Process | New Shift4 Cards with CVD. In production. Shipments to BHN warehouse start April17, completed by May 14. 041526 Finalize testing of BHN cards. 032326 RPG testing is complete. Westrock should be producing shortly. Westrock is in process of shipping out. | 4910400 |  | Est. 4/17-5/14 | C | C | A | A | C | A | C | C | A | C | A
| InComm | Shift4 w/ CVD | In Production / Shipping in Process | Awaiting Data Approvals on multiple products. Shipping schedule TBD after Final data approvals provided. Best Buy looking for Production by 3/13 for 4/5 conversion. 041526 Finalize testing of InComm cards. 032326 RPG testing is complete. Missing Best Buy in this run. Westrock should be producing shortly. Westrock is in process of shipping out. 042026 Cards are beginning to be shipped. Deadlines will be met. | 3256000 |  | TBD | C | C | A | A | C | A | C |  | A | C | A
| B2B/B2C |  |  | Review and determine volumes and timing for Fall/Winter.
| Dealer |  |  | Lauren mentioned no Holiday card so will need to place an order for standard cards. Neil to review volumes and timing to get more standard cards in stations.
| Dealer |  | Future Productuion | Review volume in fall?
COMPLETED
CARD PRODUCTION - CANADA |  |  |  |  | C = COMPLETE ¦ A = APPROVED
No. | Channel | Processor/Type | Status | Details | Overall QTY | Dates/Timing |  | Production Process - Artwork |  |  |  | Production Process - Data |  |  |  | Production Process - Packaging/Labeling |  |  | Additional Notes
[6 empty] | Ordered | Delivery | Card Artwork | Carrier Artwork | Card Proofs | Carrier Proofs | Order Data | Data Set Up Reviewed | Processor Sends Data To Printer | Data Proof Testing | Packaging/ Labeling Set Up | Review Label Proofs | Production Label Proofs Approved
| Dealer | Shift4 w/NO CVD | In Testing with Shell | Shell Dealer holding on Shell testing. 04/06 Running low on Dealer cards and will need to produce both EML and Shift4. Let's ensure we get written approval from Paul to produce more Shift4 with no CVD. 04/20 Waiting for confirmation from Shell on testing. Paul believes successful POS testing but he was going to confirm. Once successful, RPG connects with Shift4 to add CVD to data file that has been sent to Allcard. If not successful, communication to Dealers will needs to happen or small run of non-CVD. | 450000 |  |  | C | C | A | A | C | A | C |  | A | C | A
| RPG B2B/B2C | Shift4 w/ CVD | On Hold | B2B testing approved by RPG. Production on hold as of 2/27. 04/20 RPG will stick with EML cards until CVD is available. 050826 AllCard has produced RPG cards and is awaiting data. We may need to produce RPG EML cards in the interim. 051126 Prepping order for EML B2B because CVD has not been successfully completed and we are out of cards. | 265000 |  |  | C | n/a | A | n/a | C | A | C |  | A | C | A
| BHN | EML | To Start | Determine quantities for new run (which may be less than plan Shift4 run) 4/20 Asking for BHN to provide inventory requirements for EML cards. | TBD |  |  | Existing | Existing
| InComm | Shift4 w/CVD | In Motion | JF finalizing artwork/approvals. JG working Card ID''s for Data order. All testing successfully except for InComm (non-CVD - Shift4). JW emailing to advise Incomm. Grocery channel, successful testing to be completed by June 5, 2026. Cards need to be in warehouse by August 21st for September in-stores. 031126 RPG finalizing artwork (Snapcard) before sending to Shell & InComm for approvals. 041526 Julie sending artwork to Shell and InComm by 4/17. 042026 Waiting on CVD confirmation, follow up with Shift4/Incomm to understand if there is successful testing through Shell - if yes, RPG to order data. RPG to chat with Allcard on Incomm process. | 235700
| BHN | Shift4 w/NO CVD | HOLD | Extended agrement with EML. Produce EML cards until CVD is available. | 764000
COMPLETED
| Dealer | Shift4 w/NO CVD | Complete | Shell approved production of Dealer cards with no CVD. | 330000 |  |  | C | C | A | A | C | A | C | C | A | C | A
| Dealer | EML | Complete |  | 150000 |  |  | C | C | A | A | C | A | C | C | A | C | A
| RPG | EML | Complete |  | 51000 |  |  | C | n/a | A | n/a | C | A | C | C | A | C | A
| BHN | EML | Complete |  | 55000 |  |  | C | C | A | A | C | A | C | C | A | C | A

## CARD OVERVIEW
CARD PRODUCTION PRODUCT OVERVIEW
SHELL US | [5 empty] | SHELL US - SPECIALITY | [5 empty] | SHELL CANADA
Dealer
Image | Item | Vendor Proof Number | Package | Scratch Off | Notes | Image | Item | Vendor Proof Number | Package | Scratch Off | Notes | Image | Item | Vendor Proof Number | Card Quantity | Package | Scratch Off | Notes
#VALUE! | Dealer – Standard $25 | Westrock | Card on Carrier with App QR Code | Card Number & PIN |  | #VALUE! | RPG – B2B Grand Central $25 T2 | PLI | Card only | PIN Only |  | #VALUE! | Dealer – Standard $25 | Allcard |  | Card in Carrier with App QR Code | Card Number & PIN
#VALUE! | Dealer – Standard $50 | Westrock | Card on Carrier with App QR Code | Card Number & PIN |  | #VALUE! | RPG – B2B Grand Central $50 T2 | PLI | Card only | PIN Only |  | #VALUE! | Dealer – Standard $50 | Allcard |  | Card on Carrier with App QR Code | Card Number & PIN
#VALUE! | Dealer – Standard $100 | Westrock | Card on Carrier with App QR Code | Card Number & PIN |  | #VALUE! | RPG – B2B Grand Central $100 T2 | PLI | Card only | PIN Only |  | #VALUE! | Dealer – Standard $100 | Allcard |  | Card on Carrier with App QR Code | Card Number & PIN
3rd Party - AAP
Image | Item | Vendor Proof Number | Package | Scratch Off | Notes | Image | Item | Vendor | Package | Scratch Off | Notes | Image | Item | Vendor Proof Number | Card Quantity | Package | Scratch Off | Notes
| BHN – Standard $25-$250 | Westrock | Secure Pack with App QR Code | PIN |  | #VALUE! | RPG – B2B Seasons $25 T2 | PLI | Card only | PIN Only | Good |  | BHN – Standard $25, $50, $100 | Allcard |  | Secure Pack | Partial Card Number / No PIN | EML PRODUCT
#VALUE! | [5 empty] | #VALUE! | RPG – B2B Seasons $50 T2 | PLI | Card only | PIN Only | Good | #VALUE! | InComm – Standard $25-$250 + $25, $50, $100 | Allcard |  | SnapCard | Card Number & PIN
| InComm – Standard $25-$250 | Westrock | Card on Carrier with App QR Code | PIN |  | #VALUE! | RPG – B2B Seasons $100 T2 | PLI | Card only | PIN Only | Good |  | BHN – Standard $25-$250 | Allcard |  | Secure Pack | Card Number & PIN | SHIFT4 PRODUCT ON HOLD – CONTINUE WITH EXISTING EML
#VALUE!
RPG
Image | Item | Vendor Proof Number | Package | Scratch Off | Notes | Image | Item | Vendor | Package | Scratch Off | Notes | Image | Item | Vendor Proof Number |  | Package | Scratch Off | Notes
#VALUE! | RPG B2B – Standard Nondenom | Westrock |  | PIN |  | #VALUE! | RPG – B2B Johnnys $999 T2 | PLI | Card only | PIN Only | Good | #VALUE! | RPG B2B – Standard | Allcard |  |  | No PIN | Continue using EML
#VALUE! | RPG B2B – Reloadable Nondenom | Westrock |  | PIN | [7 empty] | #VALUE! | RPG Consumer – Standard | Allcard |  |  | No PIN | Continue using EML
#VALUE! | RPG B2B – Holiday Nondenom | Westrock |  | PIN |  | Image | Item | Vendor | Package | Scratch Off | Notes | #VALUE! | RPG B2B – Standard | Allcard |  |  | PIN | Shift4 product on hold until CVD
#VALUE! | RPG Consumer – (Reloadable) Main Design | RPG |  | PIN | Being replaced to mirror B2B Reloadable | #VALUE! | RPG – Shell B2B Reloadable POD T2 | PLI | Card only | PIN Only | Good | #VALUE! | RPG Consumer – Standard + Various Designs | Allcard |  |  | PIN | Shift4 product on hold until CVD
#VALUE! | RPG Consumer – (Reloadable) Various Designs | RPG |  | PIN | Plans to update images Q2 2026 | #VALUE! | RPG – Shell B2B Standard POD T2 | PLI | Card only | PIN Only | Good
[6 empty] | #VALUE! | RPG – Shell B2C Reloadable POD T2 | PLI | Card only | PIN Only | Good
[6 empty] | Image | Item | Vendor | Package | Scratch Off | Notes
[6 empty] | #VALUE! | Dealer $25 POD T2 | PLI | Card only | Card Number & PIN
[6 empty] | #VALUE! | Dealer $50 POD T2 | PLI | Card only | Card Number & PIN
[6 empty] | #VALUE! | Dealer $100 POD T2 | PLI | Card only | Card Number & PIN
[6 empty] | Image | Item | Vendor | Package | Scratch Off | Notes
[6 empty] | #VALUE! | Dealer – Seasons $25 T2 | PLI | Card only | Card Number & PIN | Good
[6 empty] | #VALUE! | Dealer – Seasons $50 T2 | PLI | Card only | Card Number & PIN | Good
[6 empty] | #VALUE! | Dealer – Seasons $100 T2 | PLI | Card only | Card Number & PIN | Good
[6 empty] | Image | Item | Vendor | Package | Scratch Off | Notes
[6 empty] | #VALUE! | Dealer – Dailys $25 T2 | PLI | Card on Carrier | Card Number & PIN
[6 empty] | #VALUE! | Dealer – Dailys $50 T2 | PLI | Card on Carrier | Card Number & PIN
[6 empty] | #VALUE! | Dealer – Dailys $100 T2 | PLI | Card on Carrier | Card Number & PIN